## 📊 Dashboard
KT Onboarding Enterprise — B2 Onboarding Journey Builder
Module Tracker ¦ v1.0 ¦ April 2026 ¦ Salesforce AppExchange Managed Package
📦 Module Summary by Feature
Feature ID | Feature Name | Total Tasks | Story Points | P1 Critical | P2 High | P3 Med/Low | Status
B2.1 | Journey Canvas & Designer (LWC) | 7 | 32 | 3 | 4 | 0 | Not Started
B2.2 | Flow Orchestration Runtime | 6 | 37 | 6 | 0 | 0 | Not Started
B2.3 | Custom Objects & Data Model | 3 | 8 | 3 | 0 | 0 | Not Started
B2.4 | SLA Engine & Escalation | 4 | 18 | 3 | 1 | 0 | Not Started
B2.5 | Gate Signal Integrations | 6 | 18 | 5 | 1 | 0 | Not Started
B2.6 | Bulk & Re-Trigger Services | 4 | 20 | 0 | 4 | 0 | Not Started
B2.7 | Headless 360 (MCP + AXL + Agent Script) | 9 | 35 | 0 | 7 | 2 | Not Started
B2.8 | React Canvas (Beta) | 2 | 14 | 0 | 0 | 2 | Not Started
B2.9 | Testing & UAT | 3 | 15 | 3 | 0 | 0 | Not Started
TOTAL | All Features | 44 | 197 | 23 | 17 | 4
⏱️ Time Estimates by Feature
Feature ID | Feature Name | AI Dev (hrs) | Buffer (25%) | Total Hrs | Total Days (÷8)
B2.1 | Journey Canvas & Designer (LWC) | 48 | 12 | 60 | 7.5
B2.2 | Flow Orchestration Runtime | 62.5 | 15.625 | 78.125 | 9.7656
B2.3 | Custom Objects & Data Model | 12 | 3 | 15 | 1.875
B2.4 | SLA Engine & Escalation | 31 | 7.75 | 38.75 | 4.8438
B2.5 | Gate Signal Integrations | 30 | 7.5 | 37.5 | 4.6875
B2.6 | Bulk & Re-Trigger Services | 32.5 | 8.125 | 40.625 | 5.0781
B2.7 | Headless 360 (MCP + AXL + Agent Script) | 72 | 18 | 90 | 11.25
B2.8 | React Canvas (Beta) | 30 | 7.5 | 37.5 | 4.6875
B2.9 | Testing & UAT | 33 | 8.25 | 41.25 | 5.1562
TOTAL | All Features | 351 | 87.75 | 438.75 | 54.8438
🗓️ Sprint Timeline
Sprint 2 | Sprint 3 | Sprints 4-6 | Sprint 7 | Sprint 9
Canvas & Designer | Runtime & SLA | Integration Hardening | Headless 360 | React Canvas Beta
9 tasks | 15 tasks | 9 tasks | 8 tasks | 3 tasks
🔑 Priority Legend
P1 - Critical | P2 - High | P3 - Medium | P4 - Low
🗓️ Sprint Colour Legend
Sprint 2 | Sprint 3 | Sprints 4-6 | Sprint 7 | Sprint 9

## 📋 All Tasks
KT Onboarding Enterprise — B2 Onboarding Journey Builder ¦ Module Task Tracker ¦ v1.0 ¦ April 2026
Section: B2 ¦ Category: Journey Orchestration ¦ Platform: Salesforce AppExchange Managed Package
Task ID | Section | Feature ID | Category | Feature Name | Task Name | Description | Tech Layer | Priority | Status | Assigned To | Sprint | Start Date | Due Date | Effort (Pts) | AI Dev (hrs) | Buffer (25%) | Total Time (hrs) | % Complete | Dependencies | Notes / Blockers
B2-T001 | B2 | B2.1 | Journey Orchestration | Journey Canvas & Designer (LWC) | Build ktJourneyBuilderCanvas LWC | SVG canvas with drag/drop stage nodes, connection arrows, zoom/pan controls, undo/redo (50 steps), auto-layout algorithm, state serialisation to JSON | LWC | P1 - Critical | Not Started |  | Sprint 2 |  |  | 8 | 12 | 3 | 15 | 0
B2-T002 | B2 | B2.1 | Journey Orchestration | Journey Canvas & Designer (LWC) | Build ktJourneyStageNode LWC | Individual stage card with type icon, settings panel, task drop zone, inline SLA config, rename, delete | LWC | P1 - Critical | Not Started |  | Sprint 2 |  |  | 5 | 7.5 | 1.875 | 9.375 | 0 | B2-T001
B2-T003 | B2 | B2.1 | Journey Orchestration | Journey Canvas & Designer (LWC) | Build ktTaskLibraryPanel LWC sidebar | Drag-and-drop task palette covering all 12 task types and sub-flow library chips, filterable by domain tag | LWC | P1 - Critical | Not Started |  | Sprint 2 |  |  | 5 | 7.5 | 1.875 | 9.375 | 0 | B2-T001
B2-T004 | B2 | B2.2 | Journey Orchestration | Flow Orchestration Runtime | Build KT_JourneyTemplateService.cls | Apex service: save/load/validate/version/clone journey JSON, enforce JSON schema, auto-increment version, prevent activation of invalid templates | Apex | P1 - Critical | Not Started |  | Sprint 2 |  |  | 5 | 7.5 | 1.875 | 9.375 | 0 | B2-T007
B2-T005 | B2 | B2.1 | Journey Orchestration | Journey Canvas & Designer (LWC) | Build ktJourneyTemplateGallery LWC | Gallery view of all active templates: filter by domain/persona, clone creates draft copy, activate sets Status=Active, archive, preview | LWC | P2 - High | Not Started |  | Sprint 2 |  |  | 4 | 6 | 1.5 | 7.5 | 0 | B2-T004
B2-T006 | B2 | B2.1 | Journey Orchestration | Journey Canvas & Designer (LWC) | Build KT_JourneyBuilderController.cls | Apex wire methods for canvas LWC: getTemplates, getTemplate, getSubFlows, saveTemplate, activateTemplate, cloneTemplate | Apex | P2 - High | Not Started |  | Sprint 2 |  |  | 3 | 4.5 | 1.125 | 5.625 | 0 | B2-T004
B2-T007 | B2 | B2.3 | Journey Orchestration | Custom Objects & Data Model | Create KT_Journey_Template__c and KT_Journey_Stage__c custom objects | All fields documented in design doc: Template JSON (131k LTA), Domain/Persona picklists, Version, Status, Stage_Count, Task_Count, OWD=Private, FLS configured | Objects / Data Model | P1 - Critical | Not Started |  | Sprint 2 |  |  | 3 | 4.5 | 1.125 | 5.625 | 0
B2-T008 | B2 | B2.3 | Journey Orchestration | Custom Objects & Data Model | Create KT_Task__c custom object | All fields: Task_Type picklist (12 values), Status, Assignee, Assignee_Type, SLA_Days, Gate fields (B3/B4/B5/B6), Branch_Condition__c formula, Is_Blocking__c, Parallel_Group__c, Dependency self-lookup | Objects / Data Model | P1 - Critical | Not Started |  | Sprint 2 |  |  | 3 | 4.5 | 1.125 | 5.625 | 0 | B2-T007
B2-T009 | B2 | B2.9 | Journey Orchestration | Testing & UAT | Build KT_B2_TestFactory.cls + Sprint 2 unit tests | Test data factory for all B2 objects; unit tests for ktJourneyBuilderCanvas wire methods and KT_JourneyTemplateService — min 90% coverage | Apex Tests | P1 - Critical | Not Started |  | Sprint 2 |  |  | 4 | 8 | 2 | 10 | 0 | B2-T004,B2-T006
B2-T010 | B2 | B2.2 | Journey Orchestration | Flow Orchestration Runtime | Build KT_JourneyOrchestrator.cls | Core runtime engine: reads KT_Journey_Template__c JSON, instantiates Flow Orchestration instance, maps 6 stage types to orchestration stages, maps tasks to steps, publishes KT_Journey_Started__e. Implements Queueable, bulkification-safe | Apex | P1 - Critical | Not Started |  | Sprint 3 |  |  | 8 | 12 | 3 | 15 | 0 | B2-T007,B2-T008
B2-T011 | B2 | B2.2 | Journey Orchestration | Flow Orchestration Runtime | Configure Salesforce Flow Orchestration — 6-stage master orchestration | KT_Journey_90Day_Orchestration: 6 orchestration stages (Pre-Onboarding → Day1 → Week1 → 30Day → 60Day → 90Day), sequential and parallel steps, gate Decision nodes wired to KT_Stage_Gate_Decision_Flow | Flow | P1 - Critical | Not Started |  | Sprint 3 |  |  | 8 | 16 | 4 | 20 | 0 | B2-T010
B2-T012 | B2 | B2.2 | Journey Orchestration | Flow Orchestration Runtime | Build parallel/sequential task execution logic in Flow Orchestration | Concurrent orchestration steps using Parallel_Track__c field; sequential chaining; contractor (3-stage) and vendor (2-stage) orchestration variants; branch conditions evaluated per Persona | Flow | P1 - Critical | Not Started |  | Sprint 3 |  |  | 6 | 12 | 3 | 15 | 0 | B2-T011
B2-T013 | B2 | B2.2 | Journey Orchestration | Flow Orchestration Runtime | Build KT_StageGateEvaluator.cls | Evaluates all 4 gate conditions: B3 form completion, B4 document verification, B5 identity verification, B6 compliance score vs threshold. Returns GateResult inner class with isPass + blockingReasons. Invocable method for Flow Orchestration decision step | Apex | P1 - Critical | Not Started |  | Sprint 3 |  |  | 5 | 7.5 | 1.875 | 9.375 | 0 | B2-T007,B2-T008
B2-T014 | B2 | B2.4 | Journey Orchestration | SLA Engine & Escalation | Build KT_SLAService.cls | SLA elapsed % calculation, breach status (Warning 80%/Breach 100%/Critical 150%), time remaining, escalation target routing. Called by scheduler and SLA Dashboard LWC wire adapter | Apex | P1 - Critical | Not Started |  | Sprint 3 |  |  | 5 | 7.5 | 1.875 | 9.375 | 0 | B2-T008,B2-T015
B2-T015 | B2 | B2.3 | Journey Orchestration | Custom Objects & Data Model | Create KT_SLA_Breach__c custom object + SLA tracking fields | All fields: Name (auto-number), Task lookup, Severity picklist, Breach_Timestamp, Breach_Elapsed_Pct, Escalated_To, Resolved_Date, Resolution_Duration_Days formula, Is_Resolved. Also add SLA fields to KT_Journey_Stage__c | Objects / Data Model | P1 - Critical | Not Started |  | Sprint 3 |  |  | 2 | 3 | 0.75 | 3.75 | 0 | B2-T008
B2-T016 | B2 | B2.4 | Journey Orchestration | SLA Engine & Escalation | Build KT_SLA_Monitor_Flow — scheduled every 30 minutes | Scheduled auto-launched flow: queries open tasks approaching SLA due date, calls KT_SLAService to calculate breach status, publishes KT_SLAWarning__e at 80%, KT_SLABreach__e at 100%, KT_SLACritical__e at 150% | Flow | P1 - Critical | Not Started |  | Sprint 3 |  |  | 4 | 8 | 2 | 10 | 0 | B2-T014
B2-T017 | B2 | B2.4 | Journey Orchestration | SLA Engine & Escalation | Build KT_SLA_Escalation_Flow — record-triggered on SLA_Breached__c | Record-triggered flow on KT_Task__c.SLA_Breached__c = true: determines escalation target (owner → stage owner → HR Admin → Executive), sends email + Slack notification, creates KT_SLA_Breach__c log record | Flow | P1 - Critical | Not Started |  | Sprint 3 |  |  | 4 | 8 | 2 | 10 | 0 | B2-T016
B2-T018 | B2 | B2.4 | Journey Orchestration | SLA Engine & Escalation | Build ktSLADashboard LWC | Real-time SLA health dashboard: open tasks by severity (On Track/Warning/Breach/Critical), escalation queue table, breach trend chart by stage and domain. Wire-connected to KT_Task__c aggregate SOQL via KT_SLAService | LWC | P2 - High | Not Started |  | Sprint 3 |  |  | 5 | 7.5 | 1.875 | 9.375 | 0 | B2-T014
B2-T019 | B2 | B2.2 | Journey Orchestration | Flow Orchestration Runtime | Build ktTaskChecklist LWC | Interactive task checklist per stage: task name, assignee, SLA due date, status chip, links to B3 form / B4 document / B5 verification / B6 compliance check. Platform Event real-time refresh. Manual completion toggle for non-gated tasks | LWC | P1 - Critical | Not Started |  | Sprint 3 |  |  | 5 | 7.5 | 1.875 | 9.375 | 0 | B2-T013
B2-T020 | B2 | B2.6 | Journey Orchestration | Bulk & Re-Trigger Services | Build KT_Journey_Pause__c + Pause/Resume Flows | KT_Journey_Pause__c custom object (all fields: Paused_By, Pause_Reason picklist, SLA_Extension_Days, Status). KT_Journey_Pause_Flow: freeze orchestration, set tasks to Paused. KT_Journey_Resume_Flow: reactivate + extend SLA | Flow | P2 - High | Not Started |  | Sprint 3 |  |  | 5 | 10 | 2.5 | 12.5 | 0 | B2-T011
B2-T021 | B2 | B2.1 | Journey Orchestration | Journey Canvas & Designer (LWC) | Build ktConditionalBranchEditor LWC | Formula-style condition builder for journey branching: persona / domain / location / assessment score conditions. Syntax validation before save. Branch preview renders dashed path on canvas. | LWC | P2 - High | Not Started |  | Sprint 3 |  |  | 4 | 6 | 1.5 | 7.5 | 0 | B2-T001
B2-T022 | B2 | B2.1 | Journey Orchestration | Journey Canvas & Designer (LWC) | Build ktSLAConfigPanel LWC | SLA days, escalation target user lookup, notification template selector, grace period config. Used at both stage-level and task-level. Embedded in ktJourneyStageNode and ktTaskLibraryPanel settings panels | LWC | P2 - High | Not Started |  | Sprint 3 |  |  | 3 | 4.5 | 1.125 | 5.625 | 0 | B2-T002
B2-T023 | B2 | B2.6 | Journey Orchestration | Bulk & Re-Trigger Services | Build sub-flow snap-in library | Reusable sub-flow components: Standard NDA Signing, Background Check Bundle, IT Access Request Set, Compliance Training Pack. Each is a KT_Sub_Flow__c record with Task_List_JSON. KT_SubFlowService.cls CRUD + runtime resolver | LWC | P2 - High | Not Started |  | Sprint 3 |  |  | 5 | 7.5 | 1.875 | 9.375 | 0 | B2-T008
B2-T024 | B2 | B2.9 | Journey Orchestration | Testing & UAT | Sprint 3 unit tests — orchestrator, gate evaluator, SLA service | Unit tests for KT_JourneyOrchestrator, KT_StageGateEvaluator, KT_SLAService, KT_SLA flows. Minimum 90% coverage. Uses KT_B2_TestFactory for mock data | Apex Tests | P1 - Critical | Not Started |  | Sprint 3 |  |  | 5 | 10 | 2.5 | 12.5 | 0 | B2-T010,B2-T013,B2-T014
B2-T025 | B2 | B2.5 | Journey Orchestration | Gate Signal Integrations | Integrate B3 gate signals | Wire KT_Form_Response__c.Status=Submitted to KT_StageGateEvaluator via record-triggered flow. On form submission: re-evaluate form gate for parent stage, advance if all gates pass | Flow | P1 - Critical | Not Started |  | Sprints 4-6 |  |  | 3 | 6 | 1.5 | 7.5 | 0 | B2-T013
B2-T026 | B2 | B2.5 | Journey Orchestration | Gate Signal Integrations | Integrate B4 gate signals | Wire KT_Document_Request__c.Status=Verified to KT_StageGateEvaluator. Record-triggered flow on doc verification: re-evaluate document gate, publish KT_Stage_Advanced__e if all gates satisfied | Flow | P1 - Critical | Not Started |  | Sprints 4-6 |  |  | 3 | 6 | 1.5 | 7.5 | 0 | B2-T013
B2-T027 | B2 | B2.5 | Journey Orchestration | Gate Signal Integrations | Integrate B5 gate signals | Subscribe to KT_Verification_Completed__e Platform Event. Trigger gate re-evaluation via KT_StageGateEvaluator on verification status = Passed for any verification type linked to a stage gate | Platform Events | P1 - Critical | Not Started |  | Sprints 4-6 |  |  | 3 | 4.5 | 1.125 | 5.625 | 0 | B2-T013
B2-T028 | B2 | B2.5 | Journey Orchestration | Gate Signal Integrations | Integrate B6 gate signals | Subscribe to KT_Compliance_Scored__e Platform Event. Evaluate compliance score against stage threshold (Gate_Compliance_Threshold__c). Advance stage gate if score >= threshold | Platform Events | P1 - Critical | Not Started |  | Sprints 4-6 |  |  | 3 | 4.5 | 1.125 | 5.625 | 0 | B2-T013
B2-T029 | B2 | B2.6 | Journey Orchestration | Bulk & Re-Trigger Services | Build ktBulkJourneyManager LWC + KT_BulkJourneyService.cls | Multi-select table of up to 500 active journeys. Bulk actions: Launch, Pause, Resume, Advance Stage, Re-assign Owner. KT_BulkJourneyService uses Queueable chaining (50 records per job) to stay within governor limits | LWC | P2 - High | Not Started |  | Sprints 4-6 |  |  | 6 | 9 | 2.25 | 11.25 | 0 | B2-T010,B2-T020
B2-T030 | B2 | B2.6 | Journey Orchestration | Bulk & Re-Trigger Services | Build KT_JourneyReTriggerService.cls | Re-trigger a completed or skipped stage: creates new stage/task records, preserves audit trail, resets gate flags, increments Re_trigger_Count__c, prevents infinite loops (max 3 re-triggers per stage) | Apex | P2 - High | Not Started |  | Sprints 4-6 |  |  | 4 | 6 | 1.5 | 7.5 | 0 | B2-T010
B2-T031 | B2 | B2.5 | Journey Orchestration | Gate Signal Integrations | Wire B7 portal task list to ktTaskChecklist via Experience Cloud | Wire ktTaskChecklist LWC to Experience Cloud guest/authenticated user context via @wire adapter. Filters tasks by Onboardee contact ID. Real-time updates via KT_Stage_Advanced__e subscription | Experience Cloud | P1 - Critical | Not Started |  | Sprints 4-6 |  |  | 4 | 6 | 1.5 | 7.5 | 0 | B2-T019
B2-T032 | B2 | B2.5 | Journey Orchestration | Gate Signal Integrations | Publish KT_Journey_Completed__e on 90-Day stage close | On 90-Day orchestration stage completion: publish KT_Journey_Completed__e with total duration, SLA breach count. Triggers B4 document archive, B10 final analytics update, Data Cloud profile completion flag | Platform Events | P2 - High | Not Started |  | Sprints 4-6 |  |  | 2 | 3 | 0.75 | 3.75 | 0 | B2-T011
B2-T033 | B2 | B2.9 | Journey Orchestration | Testing & UAT | UAT — HR team creates journeys for 3 domains, tests branching and SLA | Structured UAT: Healthcare New Employee, FinServ Contractor, Retail Vendor personas. Test conditional branching, SLA breach escalation, pause/resume state preservation, gate evaluation with all 4 gate types, bulk operations | UAT | P1 - Critical | Not Started |  | Sprints 4-6 |  |  | 6 | 15 | 3.75 | 18.75 | 0 | B2-T025,B2-T026,B2-T027,B2-T028
B2-T034 | B2 | B2.7 | Journey Orchestration | Headless 360 (MCP + AXL + Agent Script) | Expose kt_get_journey_status MCP tool | Apex REST resource (WITH SHARING, JWT auth): input onboarding_id + include_tasks + stage_filter; output JSON stage array, completion %, next_action. 30s response cache. Register in Vibes 2.0 Unified Catalog | Agentforce / MCP | P2 - High | Not Started |  | Sprint 7 |  |  | 5 | 10 | 2.5 | 12.5 | 0 | B2-T010
B2-T035 | B2 | B2.7 | Journey Orchestration | Headless 360 (MCP + AXL + Agent Script) | Expose kt_advance_journey_stage MCP tool | Apex action: input onboarding_id + stage_id + force_advance + advance_reason. Calls KT_StageGateEvaluator unless force_advance=true. Every advance logged to KT_Journey_Audit__c with agent identity. Restricted to KT_JourneyAdmin permission set | Agentforce / MCP | P2 - High | Not Started |  | Sprint 7 |  |  | 5 | 10 | 2.5 | 12.5 | 0 | B2-T013
B2-T036 | B2 | B2.7 | Journey Orchestration | Headless 360 (MCP + AXL + Agent Script) | Expose kt_get_overdue_journeys MCP tool | Apex REST: input domain + days_overdue; output list of journeys where any stage SLA_Elapsed_Pct > threshold. Used by HR Copilot for proactive breach surfacing and daily digest generation | Agentforce / MCP | P2 - High | Not Started |  | Sprint 7 |  |  | 4 | 8 | 2 | 10 | 0 | B2-T014
B2-T037 | B2 | B2.7 | Journey Orchestration | Headless 360 (MCP + AXL + Agent Script) | Agent Script: Stage Gate Evaluator block (deterministic) | Deterministic Agent Script block (zero LLM calls). Triggered on advance intent. Calls KT_StageGateEvaluator via Apex Action. Returns structured blocking reason list rendered as natural language by HR Copilot. All logic is pure rules-based Apex. | Agent Script | P2 - High | Not Started |  | Sprint 7 |  |  | 4 | 10 | 2.5 | 12.5 | 0 | B2-T013,B2-T035
B2-T038 | B2 | B2.7 | Journey Orchestration | Headless 360 (MCP + AXL + Agent Script) | Migrate Journey Builder agents to Vibes 2.0 Unified Catalog | Register KT_Journey_Stage__c + KT_Task__c as Unified Catalog context objects. Register kt_get_journey_status, kt_advance_journey_stage, kt_get_overdue_journeys tools with capability descriptions and I/O schemas. Register KT_SLABreach__e event feed for HR Copilot proactive alerts | Agentforce / MCP | P2 - High | Not Started |  | Sprint 7 |  |  | 4 | 8 | 2 | 10 | 0 | B2-T034,B2-T035,B2-T036
B2-T039 | B2 | B2.7 | Journey Orchestration | Headless 360 (MCP + AXL + Agent Script) | AXL: kt_journey_progress_card | Slack/Teams AXL card: current stage, completion %, SLA status bar, next required action, direct link to HR Admin journey view. Auto-posted to manager's Slack on each stage advance via KT_Stage_Advanced__e subscription | Agentforce / MCP | P2 - High | Not Started |  | Sprint 7 |  |  | 4 | 8 | 2 | 10 | 0 | B2-T034
B2-T040 | B2 | B2.7 | Journey Orchestration | Headless 360 (MCP + AXL + Agent Script) | AXL: kt_sla_alert_card | SLA breach alert AXL card: breached task name, assignee, elapsed %, days overdue, escalate and reassign action buttons. Fires on KT_SLABreach__e. Respects Einstein Trust Layer — no PII in card title | Agentforce / MCP | P2 - High | Not Started |  | Sprint 7 |  |  | 3 | 6 | 1.5 | 7.5 | 0 | B2-T036
B2-T041 | B2 | B2.7 | Journey Orchestration | Headless 360 (MCP + AXL + Agent Script) | AXL: kt_task_action_card | Task activation notification AXL card: task name, due date, action button linking to B7 portal form/document/verification step. Supports quick-complete for manual Task_Type tasks directly from Slack/Teams | Agentforce / MCP | P3 - Medium | Not Started |  | Sprint 7 |  |  | 3 | 6 | 1.5 | 7.5 | 0 | B2-T035
B2-T042 | B2 | B2.8 | Journey Orchestration | React Canvas (Beta) | React Journey Builder canvas | React component using Vibes 2.0 React runtime: production-parity feature set with LWC canvas (drag/drop, sub-flow insert, conditional branch, SLA config). Feature-flagged A/B vs LWC canvas per org. | Agentforce / MCP | P3 - Medium | Not Started |  | Sprint 9 |  |  | 10 | 20 | 5 | 25 | 0 | B2-T001,B2-T038
B2-T043 | B2 | B2.7 | Journey Orchestration | Headless 360 (MCP + AXL + Agent Script) | AXL: kt_bulk_status_summary — daily digest | Daily digest AXL card for HR Managers: total active journeys, stage distribution, SLA breach count, top 3 blocked journeys by days overdue. Sent at 8 AM local time via KT_SLAScheduler | Agentforce / MCP | P3 - Medium | Not Started |  | Sprint 9 |  |  | 3 | 6 | 1.5 | 7.5 | 0 | B2-T036
B2-T044 | B2 | B2.8 | Journey Orchestration | React Canvas (Beta) | Custom Scoring Evals for journey gate accuracy | Early Access: custom evaluation framework measuring gate evaluation accuracy — false positives/negatives on stage advance decisions. Feeds back to Agent Script block tuning | UAT | P3 - Medium | Not Started |  | Sprint 9 |  |  | 4 | 10 | 2.5 | 12.5 | 0 | B2-T037,B2-T042

## 📅 Sprint Plan
KT Onboarding Enterprise — B2 Onboarding Journey Builder ¦ Sprint Plan
Sprint delivery mapped to B2 feature areas ¦ Sprint 2 → Sprint 9
Sprint | Theme | Total B2 Tasks | P1 Tasks | P2 Tasks | Story Points | Status | Key B2 Deliverables | Headless 360 Notes | Key Dependencies
Sprint 2 | Canvas & Designer | 9 | 7 | 2 | 40 | Not Started | ktJourneyBuilderCanvas LWC (SVG drag/drop), ktJourneyStageNode, ktTaskLibraryPanel, KT_JourneyTemplateService.cls, ktJourneyTemplateGallery, KT_Journey_Template__c & KT_Journey_Stage__c & KT_Task__c objects, Sprint 2 unit tests | No Headless 360 items in Sprint 2 | B1 must have created KT_Journey_Stage__c and KT_Task__c records before B2 canvas is testable
Sprint 3 | Runtime & SLA | 15 | 10 | 5 | 74 | Not Started | KT_JourneyOrchestrator.cls, 90-Day Flow Orchestration (6 stages), parallel execution, KT_StageGateEvaluator.cls, KT_SLAService.cls, KT_SLA_Breach__c object, SLA Monitor/Escalation Flows, ktSLADashboard, ktTaskChecklist, Pause/Resume, ktConditionalBranchEditor, sub-flow library | No Headless 360 items in Sprint 3 | B1 DIE fully operational (Sprint 2); Flow Orchestration licence enabled in org
Sprints 4-6 | Integration Hardening | 9 | 6 | 3 | 34 | Not Started | B3/B4/B5/B6 gate signal integrations, ktBulkJourneyManager LWC, KT_BulkJourneyService.cls, KT_JourneyReTriggerService.cls, B7 portal wire, KT_Journey_Completed__e publish, UAT across 3 domains | No Headless 360 items in Sprints 4-6 | B3 Smart Forms (Sprint 3), B4 Document CLM (Sprint 4), B5 Verification (Sprint 5), B6 Compliance (Sprint 2) must be deployed
Sprint 7 | Headless 360 | 8 | 0 | 7 | 32 | Not Started | kt_get_journey_status MCP tool, kt_advance_journey_stage MCP tool, kt_get_overdue_journeys MCP tool, Agent Script Stage Gate Evaluator (deterministic), Vibes 2.0 Unified Catalog registration, kt_journey_progress_card AXL, kt_sla_alert_card AXL, kt_task_action_card AXL | B2 is a primary Sprint 7 contributor: 3 MCP tools + 3 AXL cards + 1 Agent Script block. All agents migrated to Vibes 2.0. SLABreach event feed registered as proactive HR Copilot alert. | All B2 runtime tasks (Sprint 3) complete; MuleSoft Agent Registry configured (B11 Sprint 7)
Sprint 9 | React Canvas Beta | 3 | 0 | 0 | 17 | Not Started | React Journey Builder canvas (Vibes 2.0 React runtime), kt_bulk_status_summary AXL daily digest, Custom Scoring Evals for gate accuracy (Early Access) | React canvas uses Vibes 2.0 natural language journey generation — text description → template JSON via LLM. A/B feature flag vs LWC canvas per org. | Sprint 7 Vibes 2.0 Unified Catalog registration complete; React Vibes 2.0 Early Access enabled

## 🔗 Integration Reference
KT B2 — Cross-Feature Integration Reference
Gate signal integrations and downstream consumers for B2 Onboarding Journey Builder
Feature | Direction | Integration Point | Mechanism | Sprint | Notes
B1 — Domain Intelligence Engine | → B2 RECEIVES | KT_Journey_Stage__c + KT_Task__c records created on KT_Onboarding__c insert; KT_Journey_Template__c ID populated | B1 Apex trigger creates records; KT_JourneyOrchestrator reads on KT_Onboarding__c after-insert | Sprint 1–2 | B1 is the only upstream input to B2. Without B1, no journey can be instantiated. B1 must be fully operational before B2 runtime testing.
B3 — Smart Form Builder | → B2 RECEIVES (gate signal) | KT_Form_Response__c.Status = Submitted for forms linked to task Gate_Form_ID__c | Record-Triggered Flow on KT_Form_Response__c insert/update; calls KT_StageGateEvaluator.cls | Sprint 4 | Form gate re-evaluated on each submission. Stage advances if all 4 gates now satisfied.
B4 — Document CLM | → B2 RECEIVES (gate signal) | KT_Document_Request__c.Status = Verified for document types matching Gate_Document_Type__c on KT_Task__c | Record-Triggered Flow on KT_Document_Request__c update; gate re-evaluation | Sprint 4 | Document gate unblocks stage when all required document types verified. Cascade to KT_Stage_Advanced__e if all gates pass.
B5 — Identity & Credential Verification | → B2 RECEIVES (gate signal) | KT_Verification__c.Status = Passed for verification types matching Gate_Verification_Type__c | KT_Verification_Completed__e Platform Event subscription; triggers KT_StageGateEvaluator | Sprint 5 | Verification gate evaluated on Platform Event receipt. Background check cleared = gate passes for that type.
B6 — Compliance Engine | → B2 RECEIVES (gate signal) | KT_Compliance_Check__c compliance score updates; score evaluated against Gate_Compliance_Threshold__c on KT_Journey_Stage__c | KT_Compliance_Scored__e Platform Event; KT_StageGateEvaluator checks score >= threshold | Sprint 5 | Compliance gate is the final gate — only evaluated after form/doc/verification gates pass. Minimum score is per-stage configurable.
B3 — Smart Form Builder | B2 GIVES → | KT_Task__c records with Task_Type=Form and Gate_Form_ID__c set — tells B3 which form to surface per task; stage activation notifies B3 | KT_Journey_Started__e + KT_Stage_Advanced__e event subscriptions in B3 | Sprint 3 | B2 provides the 'what form is needed' signal. B3 owns form rendering and submission. B2 only reads completion status.
B4 — Document CLM | B2 GIVES → | KT_Task__c records with Gate_Document_Type__c set — tells B4 which document types to request for each stage; journey context for document naming | KT_Task__c record insert (on journey instantiation); KT_Stage_Advanced__e event | Sprint 4 | B2 provides required document type list. B4 owns document generation, e-sign, and vault storage. B2 only reads verification status.
B5 — Identity & Credential Verification | B2 GIVES → | KT_Task__c records with Gate_Verification_Type__c — triggers B5 to initiate verification workflows; Pre-Onboarding stage activation = start verifications | KT_Task__c insert; KT_Journey_Started__e event triggers B5 verification orchestrator | Sprint 5 | Pre-Onboarding stage activating is the signal for B5 to begin identity/background check orchestration.
B6 — Compliance Engine | B2 GIVES → | Stage advance signals — tells B6 a new stage is active, compliance checks for that stage should begin; compliance threshold passed from stage definition | KT_Stage_Advanced__e Platform Event subscription in B6 | Sprint 5 | Each stage activation triggers B6 to evaluate applicable compliance rules for that stage type + domain + persona combination.
B7 — Onboardee Portal | B2 GIVES → | Live journey status: all stages + tasks with statuses, due dates, completion. Stage advance notifications. Real-time task checklist for onboardee self-service. | KT_Journey_Started__e + KT_Stage_Advanced__e events; ktTaskChecklist LWC wired via Experience Cloud | Sprint 4 | B7 portal is the onboardee's view of B2 data. ktTaskChecklist LWC is shared between HR Admin App and B7 Experience Cloud portal.
B8 — IT & Equipment Provisioning | B2 GIVES → | KT_Task__c records with Task_Type=IT — triggers B8 to initiate system access and equipment provisioning workflows | KT_Task__c insert (record-triggered flow) + KT_Stage_Advanced__e | Sprint 5 | IT tasks in Pre-Onboarding stage automatically trigger B8 provisioning flows. Start date from KT_Onboarding__c drives provisioning timeline.
B9 — Training & LMS | B2 GIVES → | KT_Task__c records with Task_Type=Training — triggers B9 to enroll onboardee in required courses on Week 1 and review stage activations | KT_Task__c insert + KT_Stage_Advanced__e for Week 1 and 30/60/90-Day stages | Sprint 5 | Training enrollment is stage-triggered. Week 1 activation = mandatory training. 30-Day activation = progress check and additional courses.
B10 — Analytics & Reporting | B2 GIVES → | All KT_Journey_Stage__c, KT_Task__c, KT_SLA_Breach__c records + all 7 B2 Platform Events for real-time dashboard updates | Direct object queries (B10 CRM Analytics) + Platform Event subscriptions | Sprint 6 | B10 is a pure consumer of B2 data. No gate signals flow back from B10 to B2. B10 queries live B2 objects for all KPIs.
B11 — Integrations & Open API | B2 GIVES → | kt_get_journey_status + kt_advance_journey_stage + kt_get_overdue_journeys MCP tools exposed via Flex Gateway for external system consumption | MCP tool REST endpoints registered in Vibes 2.0 Unified Catalog + MuleSoft Agent Registry | Sprint 7 | External HR systems can query journey status and advance stages programmatically via KT Open API using the MCP tool endpoints.